## Input
Cost Effective Alternate Methods for Steel Bridge Paint System Maintenance
FHWA Contract No. DTFH61-97-C-00026
Cost Model Input Page
Use this page to input various painting options. View model results on the "Output" page. Compare various options with the "Comparison Page"
A variable input parameter
An input selection
Item | Input | Description
Bridge Square Footage | 25000 | The paintable square footage (SF) of the bridge. Suggested minimum is 5,000. A "typical" 2-lane bridge over a divided highway may be 15,000 SF.
percent deteriorated | 30% | The percent area of the paintable area that is corroded through the coating. Typical deterioration for an overcoat project is less than 10%. Deterioration greater than 10% is seen on some paint removal projects. Deterioration over 25% may slow cleaning production rates compared to the default rates in this program.
Forman | 1 | The number of crew foremen working this project. Typically one.
Blaster/Painter | 4 | The total number of blasters and painters working this project. Typically four to six.
Helper | 2 | The total number of helpers or apprentice workers for this project. Typically one to three.
Average Labor Rate | 26 | The weighted average hourly labor rate for the total of all Foremen, Painters, and Helpers. This varies by region within the United States. Enter 26.00 as an approximate median number.
Hours/Day | 8 | The number of hours the crew works each day. Varies by hours crew is provided access to the jobsite. Average is 8 hours per day.
Lead in coating | Yes | Select if the existing coating contains lead. This relates mostly to disposal, and LH&S costs.
Washing | Yes | Select if a pre-wash of the bridge is required prior to additional surface preparation. This is a low pressure (<5,000 psi) wash with water collection and disposal.
Dehumidification | No | Select if the contained area will be dehumidified.
Pretox | No | Select if lead is in the coating and a pre-applied lead stabilizer will be used.
Blastox | No | Select if lead is in the coating and an abrasive additive will be used.
Rapid Deployment | No | Select if a rapid deployment set-up and schedule are to be used.
Stripe Coat | Yes | Select if a stripe coat is applied (default is yes)
Full Removal Surface Preparation |  | Select a single surface preparation method from the choices below. Each option has an associated production rate.
| 1 | Preparation Method | Production Rate | Description
0. Spot-Sweep Preparation
|  | 1. Once Through Abrasive | 100 | Benchmark removal method for this study. Common removal rate is 100 SF/MH. Typical range may be from 50 to 250 SF/MH.
|  | 2. ElectroStrip | 40 | Direct current removal method for coatings over steel. Rate of 40 SF/MH is from this study. Estimated production range may be from 20 to 100 SF/MH.
|  | 3. Recyclable Steel Grit | 200 | Products like "Metgrain." Removal rate of 200 is average for sites visited in this study. Typical range may be from 50 to 250 SF/MH.
|  | 4. Water Jetting | 100 | Ultra-High pressure water jetting using hand held lances. Rate of 100 SF/MH is an average of 3 site visits. Typical range may be from 75 to 150 SF/MH.
|  | 5. Grit Injected Water Jetting | 100 | Variable pressure water jetting with abrasive injection. Rate of 100 SF/MH is from this study. Typical range may be from 75 to 150 SF/MH.
|  | 6. Torbo Wetblast System | 91 | Production rate of 91 is from this study. Typical range may be from 50 to 200 SF/MH.
Spot-Sweep Surface Preparation |  | Select a single surface preparation method from the choices below. Each option has an associated production rate.
| 0 | Preparation Method | Production Rate | Description
0. Full Removal Preparation
|  | 1. Hand Tool Cleaning | 10 | Benchmark spot preparation method for this study. Typical production rate is 10 SF/MH for cleaning of "spots" only. These numbers vary greatly depending upon the condition of the bridge.
|  | 2. Water Jetting | 135.187 | Calculation based on data from this study. = "0.019*Deterioration^2-2.6371*Deterioration+197.2"
|  | 3. Brush Blast (expendable grit) | 63.1333 | Calculation based on data from this study. = "18.94/percent deteriorated"
|  | 4. Grit Injected Water Jetting | 63.1333 | Calculation based on data from this study. = "18.94/percent deteriorated"
|  | 5. Recyclable Steel Grit | 200 | Rate to sweep all surfaces. 200 SF/hr was used for this study
|  | 6. Water Injected Blasting (Torbo) | 150 | Rate to sweep all surfaces. 150 SF/hr was used for this study
|  | 7. Vacuum Blasting | 80 | Rate to clean at individual spots of degradation only. 80 SF/hr was used for this study.
Staging/Containment Options |  | Select a single staging and containment option from the choices below. Each option has an associated speed factor and cost factor.
| 1 | Staging/Containment Option | Hours per location | Description
|  | 1. Lift Trucks | 0.75 | Lift Trucks are a completely mobile option. All staging is removed after each work shift. Enter the hours required to complete one set-up / teardown cycle per work location. (This study = .75 hrs.)
|  | 2. Safe-Span Platform | 200 | Enter SF built by the entire crew per hour (This study = 200 SF/hr.)
|  | 3. Suspended Rigid Platform | 320 | Enter SF built by the entire crew per hour. (This study = 320 SF/hr.)
|  | 4. ARK Mobile Platform System | 0.5 | Hours required to set-up and remove an ARK platform per shift (This study = .5 hrs.)
Coating System Options |  | Select a single Coating System from the choices below.
| 4 | Coating System Type | Description
|  | 1. Three Coat System | Primer over bare metal plus two full coats
|  | 2. Two Coat System | Primer over bare metal plus one full coat
|  | 3. Metallizing | 176.4 | Wire arc spray. Enter SF sprayed per hour per worker. (This study = 176.4 SF/hr.)
|  | 4. Metallizing with Sealer | 176.4 | Wire arc spray with full coat airless sprayed sealer
Coating Application Options |  | Select a single Coating Application Option from the choices below. Each option has an associated production factor.
| 4 | Application Option | Production Rate | Description
|  | 1. Brush | 1500 | SF per hour applied by brushing (This study = 1500 SF/hr.)
|  | 2. Roller | 1875 | SF per hour applied by rolling (This study = 1875 SF/hr.)
|  | 3. Conv Spray | 2400 | SF per hour applied with conventional spray (This study = 2400 SF/hr.)
|  | 4. Airless Spray | 3750 | SF per hour applied with airless spray (This study = 3750 SF/hr.)
error checks ##=true 0=false
0 | DATA CONFLICT! - "Lead in coating" is not selected, with Blastox or Pretox.
0 | DATA CONFLICT! - "Blastox" and "Pretox" are selected simultaneously.
0 | DATA CONFLICT! - A "full removal" and a "spot preparation" are selected at the same time.
0 | CHECK YOUR DATA! - "Metallizing" is selected with a "spot" surface preparation.
Selection Lists | 0
Yes | 1
No | 2
3
4
5
6
7
8

## Output
Cost Effective Alternate Methods for Steel Bridge Paint System Maintenance
FHWA Contract No. DTFH61-97-C-00026
Cost Model Spreadsheet - Results Page
For a Bridge Project with:
| 25000 | Paintable Square Feet
| 30% | Percent Area Deteriorated
| 7 | Persons in the Work Crew
The Costs to:
Contain the bridge using Lift Trucks
Perform full removal with once through abrasive
Arc spray metallizing with an airless applied seal coat
are given below.
|  |  | Item Cost | Item Percentage | Cost / SF | Select below to send results to the "Comparison Page"
|  | Labor Cost | 72072 | 27.76% | 2.8829
|  | Waste Disposal | 48976.875 | 18.87% | 1.9591
|  | Materials | 42378.75 | 16.33% | 1.6951
|  | Production Equipment | 30204.1697 | 11.64% | 1.2082
|  | Lead Health and Safety | 8925 | 3.438% | 0.357
|  | Staging and Containment | 10390.3276 | 4.003% | 0.41561
|  | Project Insurance | 12776.8273 | 4.922% | 0.51107
|  | Profit | 33858.5924 | 13.04% | 1.3543
|  | Total Cost | 259582.5421 | 100% | 10.3833
1
1 | Perform full removal with once through abrasive
2 | Perform full removal with ElectroStrip
3 | Perform full removal with recyclable steel grit
4 | Perform full removal using water jetting
5 | Perform full removal with grit injected water jetting
6 | Perform full removal with the Torbo wetblast system
11 | Perform spot cleaning with hand tools
12 | Perform spot cleaning using water jetting
13 | Perform spot cleaning with an expendable grit brush blast
14 | Perform spot cleaning with grit injected water jetting
15 | Perform spot cleaning with recyclable steel grit
16 | Perform spot cleaning using water injected blasting (Torbo)
17 | Perform spot cleaning using vacuum blasting
1 | Lift Trucks
2 | a Safe-Span Platform
3 | a Suspended Rigid Platform
4 | an ARK Mobile Platform System
1 | three coat system
2 | two coat system
1 | Brush apply a
2 | Roll on a
3 | Conventional spray apply a
4 | Airless spray apply a
Arc spray apply unsealed metallizing
Arc spray metallizing with an airless applied seal coat

## Comparison Page
Cost Effective Alternate Methods for Steel Bridge Paint System Maintenance
FHWA Contract No. DTFH61-97-C-00026
| Option 1 | Option 2 | Option 3
Labor Cost | 2.3587 | 2.3587 | 2.184
Waste Disposal | 1.9591 | 1.9591 | 0.13867
Materials | 0.91353 | 0.91353 | 1.3522
Production Equipment | 0.75561 | 0.75561 | 1.0199
Lead Health and Safety | 0.303 | 0.303 | 0.285
Staging and Containment | 0.32834 | 0.32834 | 0.32834
Project Insurance | 0.3971 | 0.3971 | 0.31849
Profit | 1.0523 | 1.0523 | 0.84399
Total Cost / SF | 8.0677 | 8.0677 | 6.4706

## Time
Time Calculations
|  | Man-Hours for Project | Logic | Crew Days | Project days
Basic Calculations | result
Br Length | 167.5
Br Width | 60
Staging Deck Area | 10050
Critical SF | 13750
SF to bare metal | 25000
Non Critical SF | 11250
Crew Size | 7
Full Removal | 1. Once Through Abrasive | 250 | 1 | 12 | 12 | 1
| 2. ElectroStrip | 625 | 0 | 29 | 0 | 2
| 3. Recyclable Steel Grit | 125 | 0 | 6 | 0 | 3
| 4. Water Jetting | 250 | 0 | 12 | 0 | 4
| 5. Grit Injected Water Jetting | 250 | 0 | 12 | 0 | 5
| 6. Torbo Wetblast System | 274.7253 | 0 | 13 | 0 | 6
Spot/Sweep | 1. Hand Tool Cleaning | 750 | 0 | 35 | 0 | 1
| 2. Water Jetting | 184.929 | 0 | 9 | 0 | 2
| 3. Brush Blast (expendable grit) | 395.9873 | 0 | 18 | 0 | 3
| 4. Grit Injected Water Jetting | 395.9873 | 0 | 18 | 0 | 4
| 5. Recyclable Steel Grit | 125 | 0 | 6 | 0 | 5
| 6. Water Injected Blasting (Torbo) | 166.6667 | 0 | 8 | 0 | 6
| 7. Vacuum Blasting | 93.75 | 0 | 5 | 0 | 7
Rapid Deployment |  |  | 0 | 11 | 0
Pretox |  | 8.3333 | 0 | 1 | 0
LPWC Washing | 4kpsi | 41.6667 | 1 | 2 | 2
[7 empty] | 3-coat | 2-coat | sealer
Painting | 1. Brush | 33.3333 | 0 | 2 | 0 | 1 | 50 | 33.3333
Crit + Non-Crit Areas | 2. Roller | 26.6667 | 0 | 2 | 0 | 2 | 40 | 26.6667
25000 | 3. Conv Spray | 20.8333 | 0 | 1 | 0 | 3 | 31.25 | 20.8333
| 4. Airless Spray | 6.6667 | 1 | 1 | 1 | 4 | 20 | 13.3333 | 6.6667
| Stripe Coat | 9.6154 | 1 | 1 | 1
| Metallizing | 141.7234 | 1 | 7 | 7
Staging
Custom | 3. Suspended Rigid Platform | 31.4062 | 0 | 1 | 0 | 3
Modular
| abutment staging w/ lift trucks | 4.7109
| 1. Lift Trucks | 26.6953 | 1 | 1 | 1 | 1 | 31.4062
| 2. Safe-Span Platform | 50.25 | 0 | 2 | 0 | 2
| abutment staging w/ ARK platforms | 4.7109
| 4. ARK Mobile Platform System | 25.125 | 0 | 1 | 0 | 4 | 29.8359
Containment
Spot Prep | Hrs/move with hand vacuum cleaning | 5.2344 | 0 | 1 | 0
Full/Spot Removal | Hrs/move for full removal - dry - from LTruck | 20.9375 | 1 | 1 | 1
| Full removal - wet methods - from lift truck | 10.4688 | 0 | 1 | 0
Mob/Demob | 5 days of mob/demob for entire crew | 280 | 1 | 8 | 8
|  |  |  | Total | 33 | Project Days |  | 3 | Project Months
Time subtotals for equipment applicable to multiple scenarios:
| Recyclable Steel Grit Rig - 4 outlet |  |  |  | 0
| UHP (6 GPM) - 2 outlet |  |  |  | 0
| Grit Blast Rig - 4 outlet |  |  |  | 12
| AIWB (Grit Injection Rig) - 2 outlet |  |  |  | 0
| Torbo System - single outlet |  |  |  | 0
Note on B65: Chris Farschon: This is scaled up based on ratio of # painters to total crew size

## Materials
Materials Calculations
Surface Preparation Materials
Abrasives | lbs. / SF | SF to bare metal | Tons required | Removal Logic | Material (Gallons) | Material (Tons)
Steel Grit | 0.5 | 25000 | 6.25 | 0 |  | 0
Slag Abrasive | 10 | 25000 | 125 | 1 |  | 125
Grit in Water/Grit | 1 | 25000 | 12.5 | 0 |  | 0
Grit in Grit/Water | 3 | 25000 | 37.5 | 0 |  | 0
Vacuum Blast Grit | 1 | 25000 | 12.5 | 0 |  | 0
Water | Gal/ft2 | SF to bare metal | Gallons required
UHP Water Jetting | 1.3315 | 25000 | 33287.2244 | 0 | 0
LPWC Washing | 0.15 | 25000 | 3750 | 1 | 3750
Water in Water/Grit | 0.1233 | 25000 | 3082.5 | 0 | 0
Water in Grit/Water | 0.12 | 25000 | 3000 | 0 | 0
|  |  |  | Total Water | 3750
|  |  |  | Total Expendable Grit |  | 125
Coatings, Fuel and Residual Waste Materials
Item | Spread Rate SF / Gal | SF to Paint | Application Method | Gals Required | Logic | Material Required (gallons)
Pretox | 80 | 25000 | Airless | 312.5 | 0 | 0
Coatings
Primer | 400 | 25000 | Airless | 62.5 | 0 | 0
Topcoats | 400 | 25000 | Airless | 62.5 | 0 | 0
Metal Sealer | 400 | 25000 | Airless | 62.5 | 1 | 62.5
| lbs/SF | SF |  | lbs required |  | lbs required
Metallizing | 0.4701 | 25000 |  | 11752.5 | 1 | 11752.5
Fuel | Gal/day | Days Required |  |  |  | Fuel Total
| 120 | 33 |  | 3960 | 1 | 3960
Paint Waste Genrtd | SF to bare metal | Existing DFT | Cu Ft to Remove | Existing sp gravity | Tons of Paint
| 25000 | 17.5 | 36.4583 | 2.5 | 2.8438
Pretox Waste Gnrtd | gal used | density | tons
| 0 | 8.28 | 0
Total Solid Waste Generated |  | 127.8438 | tons
Total Liquid Waste Generated |  | 3750 | gallons

## Cost
Cost Calculations
Equipment Costs
Equipment Name | $/month | Required Logic | Number Months Required | Number Units Needed | Cost
Recyclable Steel Grit Rig - 4 outlet | 7480.2759 | 0 | 0 | 1 | 0
UHP (10 GPM) - 2 outlet | 6233.5632 | N/A | N/A | N/A | N/A
WJ Crawler/w vac. | 6233.5632 | N/A | N/A | N/A | N/A
UHP (6 GPM) - 2 outlet | 4207.6552 | 0 | 0 | 2 | 0
Compressor - for 3 crewmen | 2337.5862 | 1 | 3 | 2 | 14025.5173
Grit Blast Rig - 4 outlet | 2181.7471 | 1 | 1 | 1 | 2181.7471
ElectroStrip Machine | 2119.4115 | 0 | 0 | 1 | 0
AIWB (Grit Injection Rig) - 2 outlet | 1862.277 | 0 | 0 | 2 | 0
Water Washing - 4 outlet | 1714.2299 | 1 | 1 | 1 | 1714.2299
Torbo System - single outlet | 1055.0306 | 0 | 0 | 4 | 0
Airless (high solids) | 255.1086 | N/A | N/A | N/A | N/A
Generator (100 kW) | 779.1954 | 1 | 1 | 2 | 1558.3908
Airless Spray (regular) | 180.3058 | 1 | 1 | 2 | 360.6116
Convention Sprayer | 54.1073 | 0 | 0 | 1 | 0
Generator (2.25 kW) - for 6 crewmen | 31.1678 | 1 | 3 | 2 | 187.0069
Moister Separator | 22.5967 | 0 | 3 | 2 | 0
Blast Hoods B-88's | 19.5734 | 1 | 1 | 4 | 78.2936
Misc. Hand Tools | 119.9961 | 0 | 0 | 4 | 0
Vacuum Blast Rig - 4 outlet | 2999.9023 | 0 | 0 | 1 | 0
Vacuum Truck | 2025.9081 | 1 | 1 | 1 | 2025.9081
Decon Trailer - for leadwork | 748.0276 | 1 | 3 | 1 | 2244.0828
Truck MPT/Towing for 4 crewmen | 779.1954 | 1 | 3 | 1 | 2337.5862
Arc Spray Metallizing unit | 872.6989 | 1 | 1 | 4 | 3490.7954
|  |  |  | Equipment Cost Subtotal | 30204.1697
Staging/Containment Costs
Equipment Name | $/month | Required Logic | Number Months Required | Number Units Needed | Cost
ARK System (2 crewmen per section) | 451.9333 | 0 | 3 | 2 | 0
Ark Overpass Master | 2334.4694 | N/A | N/A | N/A | N/A
Lift Truck for 4 crewmen | 2181.7471 | 1 | 3 | 1 | 6545.2414
Dust Collector | 2337.5862 | 1 | 1 | 1 | 2337.5862
D/H Unit | 785.429 | 0 | 3 | 1 | 0
Platform to supplement LT or ARK (1$/SF) | 1 | 1 | 1 | 1507.5 | 1507.5
Safe Span | 0.4 | 0 | 3 | 10050 | 0
Plywood Platform Staging | 5000 | 0 | 1 | 3 | 0
|  |  |  | Staging Cost Subtotal | 10390.3276
Chart for SafeSpan Pricing
0.4
| $/SF/Month | size | 8 months | 9-16 months | 17+ months
| 0.4 | <50,000 | 0.4 | 0.36 | 0.32
| 0.35 | 50,000-99,999 | 0.35 | 0.32 | 0.28
| 0.3 | >100,000 | 0.3 | 0.27 | 0.24
Materials Costs
| $/unit | units | Subtotal | Total Materials
Steel Grit (per Ton) | 300 | 0 | 0
Slag Grit (per Ton) | 60 | 125 | 7500
Grit with Blastox (per Ton) | 148 | 0 | 0
Pretox (per Gallon) | 19.95 | 0 | 0
Water (per Gallon) | 0.027 | 3750 | 101.25
Paint (per Gallon) | 30 | 62.5 | 1875
Metallizing Wire (per lb.) | 1.8 | 11752.5 | 21154.5
Fuel (per Gallon) | 1.3 | 3960 | 5148
Other Misc. Items (per Day (misc. sundries each day)) | 200 | 33 | 6600
|  |  |  | Material Cost Subtotal | 42378.75
Disposal Costs
| $/unit | units | Required Logic | Cost
Barrel for solid waste disposal | 30 | 853 | 1 | 25590
Hazardous material disposal | 180 | 127.8438 | 1 | 23011.875
Non-hazardous material disposal | 60 | 127.8438 | 0 | 0
Wash water disposal | 0.1 | 3750 | 1 | 375
|  |  |  | Disposal Cost Subtotal | 48976.875
Labor Costs
| # workers | loaded rate | $/day | Days
| 7 | 39 | 2184 | 33
|  |  |  | Labor Cost Subtotal | 72072
Lead Health and Safety Costs
| $ / Item | Required Logic | Units Needed | Cost
Lead Health and Safety Plan | 500 | 1 | 1 | 500
Site Pre-Assessment | 500 | 1 | 1 | 500
High Vol. Air Monitoring | 50 | 1 | 33 | 1650
Field Tech./Emissions Observer | 75 | 1 | 33 | 2475
Lab Testing of Samples | 100 | 1 | 33 | 3300
Post Site Assessment | 500 | 1 | 1 | 500
|  |  |  | LH&S Cost Subtotal | 8925
Cost Summary
subtotal | 212947.1223
Insurance | 12776.8273
Profit | 33858.5924
Total Cost | 259582.5421
$/SF | 10.3833
Cost Breakdown
Labor Cost | 72072 | 27.76% | 2.8829
Waste Disposal | 48976.875 | 18.87% | 1.9591
Materials | 42378.75 | 16.33% | 1.6951
Production Equipment | 30204.1697 | 11.64% | 1.2082
Lead Health and Safety | 8925 | 3.438% | 0.357
Project Insurance | 12776.8273 | 4.922% | 0.51107
Profit | 33858.5924 | 13.04% | 1.3543
Staging and Containment | 10390.3276 | 4.003% | 0.41561
Total Cost | 259582.5421 | 100% | 10.3833

## Cost Variables
Background Variables page - Use this page to vary the calculation parameters for the cost model
= a changeable input parameter
Surface Preparation Equipment Costs | Initial Cost | Service Life (yrs) | Discount Rate | Total Cost | Cost per year | Cost per month (9 month year) | Notes
Recyclable Steel Grit Rig - 4 outlet | 240000 | 5 | 7% | -336612.4154 | -67322.4831 | -7480.2759
UHP (10 GPM) - 2 outlet | 200000 | 5 | 7% | -280510.3461 | -56102.0692 | -6233.5632
WJ Crawler/w vac. | 200000 | 5 | 7% | -280510.3461 | -56102.0692 | -6233.5632
UHP (6 GPM) - 2 outlet | 135000 | 5 | 7% | -189344.4836 | -37868.8967 | -4207.6552
Compressor - for 3 crewmen | 75000 | 5 | 7% | -105191.3798 | -21038.276 | -2337.5862
Grit Blast Rig - 4 outlet | 70000 | 5 | 7% | -98178.6211 | -19635.7242 | -2181.7471
ElectroStrip Machine | 68000 | 5 | 7% | -95373.5177 | -19074.7035 | -2119.4115
AIWB (Grit Injection Rig) - 2 outlet | 59750 | 5 | 7% | -83802.4659 | -16760.4932 | -1862.277
Water Washing - 4 outlet | 55000 | 5 | 7% | -77140.3452 | -15428.069 | -1714.2299
Torbo System - single outlet | 33850 | 5 | 7% | -47476.3761 | -9495.2752 | -1055.0306
Airless (high solids) | 8185 | 5 | 7% | -11479.8859 | -2295.9772 | -255.1086
Generator (100 kW) | 25000 | 5 | 7% | -35063.7933 | -7012.7587 | -779.1954
Airless Spray (regular) | 5785 | 5 | 7% | -8113.7618 | -1622.7524 | -180.3058
Convention Sprayer | 1736 | 5 | 7% | -2434.8298 | -486.966 | -54.1073
Generator (2.25 kW) - for 6 crewmen | 1000 | 5 | 7% | -1402.5517 | -280.5103 | -31.1678
Moister Separator | 725 | 5 | 7% | -1016.85 | -203.37 | -22.5967
Blast Hoods B-88's | 628 | 5 | 7% | -880.8025 | -176.1605 | -19.5734
Misc. Hand Tools | 3850 | 5 | 7% | -5399.8242 | -1079.9648 | -119.9961 | scaled to include frequent tool replacement
Vacuum Blast Rig - 4 outlet | 96250 | 5 | 7% | -134995.6041 | -26999.1208 | -2999.9023
Vacuum Truck | 65000 | 5 | 7% | -91165.8625 | -18233.1725 | -2025.9081
Decon Trailer - for leadwork | 24000 | 5 | 7% | -33661.2415 | -6732.2483 | -748.0276
Truck MPT/Towing for 4 crewmen | 25000 | 5 | 7% | -35063.7933 | -7012.7587 | -779.1954
Arc Spray Metallizing unit | 28000 | 5 | 7% | -39271.4485 | -7854.2897 | -872.6989
Days / month used to cost out equip. | 16 | Default is 16. If the equipment is used more than this many days per month, and additional month's cost is added.
Staging/Containment Equipment Costs | Initial Cost | Service Life (yrs) | Discount Rate | Total Cost | Cost per year | Cost per month (9 month year) | Notes
ARK System (2 crewmen per section) | 14500 | 5 | 7% | -20337.0001 | -4067.4 | -451.9333
Ark Overpass Master | 74900 | 5 | 7% | -105051.1246 | -21010.2249 | -2334.4694
Lift Truck for 4 crewmen | 70000 | 5 | 7% | -98178.6211 | -19635.7242 | -2181.7471
Dust Collector | 75000 | 5 | 7% | -105191.3798 | -21038.276 | -2337.5862
D/H Unit | 25200 | 5 | 7% | -35344.3036 | -7068.8607 | -785.429
Rigid platform staging (plywood) | 1 | $/SF for the platform materials, set up with unit increments of 5,000 SF. This disposable material is costed for one month only (set-up only)
SafeSpan System |  | cost of Safespan is calculated based on the safe span rental schedule located within the "cost" page calculations.
Equipment Sizing
Lift Truck Deck Area | 40 | Length | 12 | Width | 480 | SF
% Area Inaccessible to LT or ARK | 15% | %-age
ARK system Deck Area | 40 | Length | 8.5 | Width | 340 | SF
Time Required to move Containment
Spot Prep - hand/vacuum - from lift truck | 0.25 | hrs/move
Full removal - dry methods - from lift truck | 1 | hrs/move
Full removal - wet methods - from lift truck | 0.5 | hrs/move
Pre-Existing Conditions
Existing Paint DFT | 17.5 | mils | Thickness of the existing paint to be removed. Default value is 15 mils.
Existing Paint Specific Gravity | 2.5 | ratio | Specific gravity of the existing coating to be removed. Typical values range from 1.8 to 2.8. Default is 2.5
Material Costs
| cost/unit | unit
Steel Grit | 300 | Ton
Slag Grit | 60 | Ton
Grit with Blastox | 148 | Ton
Pretox | 19.95 | Gallon
Water | 0.027 | Gallon
Paint | 30 | Gallon
Fuel | 1.3 | Gallon
Other Misc. Items | 200 | Day (misc. sundries each day)
Metallizing Wire | 1.8 | pound
Material Use/Application Rates
Pretox Application Rate | 3000 | SF/Hr
Pretox usage rate | 80 | SF/gal | The ideal spreading rate at the specified WFT
PreTox dry density | 8.28 | lb./gal | density of dried Pretox used in waste tonnage calculation.
LPWC Production Rate | 600 | SF/Hr
Stripe Coat Production Rate | 2600 | Edges in SF shown / Hr
RSG usage rate | 0.5 | lb./SF | This is the average RSG consumption rate for the project NOT the amount needed to clean each SF. If new RSG is specified for a project this should be higher, if new RSG is not specified .5 lb./SF is an accurate number.
Once Through Slag usage rate | 10 | lb./SF | Average needed to clean each SF
UHP water usage rate | 3 | GPM | 1.8 | gal/SF full removal | 1.3315 | gal/SF spot work
LPWC usage rate | 0.15 | gal/SF
Water with Grit injection - Water use | 0.1233 | gal/SF
Water with Grit injection - Grit use | 1 | lb./SF
Grit blast with Water injection - Grit use | 3 | lb./SF
Grit blast with Water injection - Water use | 0.12 | gal/SF
Vacuum Blast grit use rate | 1 | lb./SF | This is the grit consumption rate for the project NOT the amount needed to clean each SF. If new grit is specified increase this amount, otherwise 1 lb./SF is a reasonable average consumption.
Paint usage rate | 400 | SF/gal | The ideal spreading rate at the specified WFT
Fuel usage rate | 120 | gal/day | For all equipment at the jobsite
wire metallizing usage rate | 0.4701 | lbs/SF | The ideal spreading rate of 85/15 at 15 mils DFT
Painting Transfer Efficiencies
Airless | 100% | percent | Typical values are 70 to 85% - default is 100%
Brush | 100% | percent | Typical values are 80 to 95% - default is 100%
Conventional | 100% | percent | Typical values are 65 to 80% - default is 100%
Roll | 100% | percent | Typical values are 80 to 90% - default is 100%
wire spray metallizing | 79% | percent | Typical values are 75 to 90% - default is based on field observation
Disposal Cost Factors
Barrel for solid waste disposal | 30 | each
Hazardous material disposal | 180 | ton
Non-hazardous material disposal | 60 | ton
Wash water disposal | 0.1 | gallon
Operating Cost Factors
Insurance (percent of project subtotal) | 6% | percent | Typical values are 4 to 10% - default is 6%
Profit (percent of all costs + insurance) | 15% | percent | Typical values are 7 to 20% - default is 15%
Labor Overhead Rate | 50% | percent | Value used to "load" base labor rate. Typical values are 35% to 75% - default is 50%
Lead Health and Safety Costs
Lead Health and Safety Plan | 500 | dollars | Variable input depending upon size and complexity of Project
Site Pre-Assessment | 500 | dollars | Variable input depending upon size and complexity of Project
High Vol. Air Monitoring | 50 | dollars | Price per day for HV monitoring. If lead is present = applies to full duration, If no lead = applies to S Prep time only.
Field Tech./Emissions Observer | 75 | dollars | Price per day for field tech. If lead is present = applies to full duration, If no lead = applies to Surface Prep time only.
Lab Testing of Samples | 100 | dollars | Price per day for sample testing. If lead is present = applies to full duration, If no lead = applies to Surface Prep time only.
Post Site Assessment | 500 | dollars | Variable input depending upon size and complexity of Project
Other Back-up notes:
| 1 | Crew days calculation takes total man-hours for an activity an divides by hours/day minus 2.5 times the number of painters. This calculation is rounded up. The 2.5 is a given # of hours/day where no production work is happening.
| 2 | The spot prep waterjetting production follows the formula "SF/Hr = 0.019*%Deterioration^2-2.6371*%Deterioration+197.2"
| 3 | The vacuum blasting spot prep production formula is "=(bridge SF*(% deteriorated/100))/vac blast production rate". This reduces the vac blast SF to the spot deterioration only.
| 4 | Rapid deployment crew days are 85% of Bridge area divided by (2.5 / RSG production * # blasters)
| 5 | Crew days for staging and containment include the entire crew working, not just number of painters as with production work operations
| 6 | The production rates for SPOT brush blast and grit injected are (18.94*% area deteriorated)
| 7 | Rapid deployment utilizes hand tools to supplement abrasive blasting.
Water jetting spot prep production
% Deterioration | SF/Hr
1 | 194.5819
2 | 192.0018
5 | 184.4895
10 | 172.729
20 | 152.058
40 | 122.116
60 | 107.374
80 | 107.832
90 | 113.761
Brush blast and grit injection SPOT prep production
% Deterioration | SF/Hr
1% | 1894
2% | 947
5% | 378.8
10% | 189.4
20% | 94.7
40% | 47.35
60% | 31.5667
80% | 23.675
90% | 21.0444